## Sprint Stats
Sprint1 | Week1 (04/03- 04/07) | Data ingestion (Batch) from RDBMS to Hadoop Lake
Sprint2 | Week2 (04/10-04/14) | Data preparation/cleansing process using Hive
Sprint3 | Week3 (04/16 - 04/20) | Data migration from Hive to ES
Sprint4 | Week4 (04/23 - 04/28) | Data Visualization using Kibana
Sprint5 | Week5 (05/01 - 05/05) | Data Visualization using Kibana
Sprint6 | Week6 (05/08 - 05/12) | Data Visualization using Kibana
Sprint7 | Week7 (05/15 - 05/19) | Testing
Sprint8 | Week8 (05/22 - 05/26) | Testing

## Sprint1
Objective | Data ingestion (Batch) from RDBMS to Hadoop Lake
| 2017-04-03 | status | Remarks
| Create a 2 node EMR cluster in amazon.Make it static ip |  | 34.203.47.144 34.203.47.234 - working install sqoop mysql>created testdb
Prepare the list of Hive tables required.
Install the generic database in the cluster
Load the test data into 2 tables
2017-04-04
Load the test data into rest of tables
Prepare the sqoop scripts for all the tables.
Execute the sqoop scripts to create the hive tables
Prepare the sqoop scripts for all the tables.
Execute the sqoop scripts to create the hive tables
2017-04-05
| Prepare a protype of the casemanager in aws as a static webpage | In progress
2017-05-01
| Complete the Data Visualization(Kibana) requirements | WIP
Complete the Data Transformation(Spark) requirements
Complete the Data ingestion(Sqoop/Hive) requirements
2017-05-02
2017-05-03
2017-05-04
2017-05-05

## Dashboard Requirements
| Requirements | Data Requirements
Dashboard name | Name of the dashboard is Casemanager. There should be a search screen on top and allow users to search based on any values eg:C201704*.Output should return with all the data with the input search value. If the input search value is not present , then it should return 'no results found'
Visualization1 | Create a Case summary with the below stats. Case Number Alert Count(s) : Case Name : Customer count : Transaction count(s) : Transaction total : Case Creation Date/Time : | Case Number should be of CYYYYMMNNNNN eg:C20170412345 Alert count,customer count and Transactions count contains only digit values Case Name contains only character values. Transaction total is of decimal type and $ should be prefixed before the amount eg:$4,656,171.50. Case creation timestamp should be of YYYY-MM-DD HH:MM:SS format. There shouldn't be any pencil or x mark in the viz board
Visualization2 | Create an Alert summary with the below stats. Case Number Alert Number : Scenario : Transaction count(s) : Transaction total : Alert creation timestamp : | Case Number should be of CYYYYMMNNNNN. Alert Number should be of ANNNNNNN eg:A1234567. Transaction total is of decimal type and $ should be prefixed before the amount eg:$4,656,171.50. Alert creation timestamp should be of YYYY-MM-DD HH:MM:SS format.
Visualization3
Visualization4
Visualization5
Visualization6
Visualization7
Visualization8
Visualization9
Visualization10

## mysql commands
create table testtable(case_id VARCHAR(30),case_identifier VARCHAR(30));
insert into testtable values(1234567,C201703021234567);

## Data mapping
Vizboard1 | target column name | source column name | source table name
Case Number | Case Number | case_identifier | cases
Alert Count(s) : | Alert Count | number_of_alerts | cases
Case Name : | Case Name | case_description | cases
Customer count : | Customer Count |  | cases
Transaction count(s) : | Transaction Count |  | cases alert_key mon_alert
Transaction total : | Transaction Total
Case Creation Date/Time : | Case timestamp | creation_timestamp