## Sprint Stats
Sprint1 | Week1 (04/03- 04/07) | Data ingestion (Batch) from RDBMS to Hadoop Lake
Sprint2 | Week2 (04/10-04/14) | Data preparation/cleansing process using Hive
Sprint3 | Week3 (04/16 - 04/20) | Data migration from Hive to ES
Sprint4 | Week4 (04/23 - 04/28) | Data Visualization using Kibana
Sprint5 | Week5 (05/01 - 05/05) | Data Visualization using Kibana
Sprint6 | Week6 (05/08 - 05/12) | Data Visualization using Kibana
Sprint7 | Week7 (05/15 - 05/19) | Testing
Sprint8 | Week8 (05/22 - 05/26) | Testing

## Sprint1
Objective | Data ingestion (Batch) from RDBMS to Hadoop Lake
| 2017-04-03 | status | Remarks
| Create a 2 node EMR cluster in amazon.Make it static ip |  | 34.203.47.144 34.203.47.234 - working install sqoop mysql>created testdb
Prepare the list of Hive tables required.
Install the generic database in the cluster
Load the test data into 2 tables
2017-04-04
Load the test data into rest of tables
Prepare the sqoop scripts for all the tables.
Execute the sqoop scripts to create the hive tables
Prepare the sqoop scripts for all the tables.
Execute the sqoop scripts to create the hive tables
2017-04-05
| Prepare a protype of the casemanager in aws as a static webpage | In progress
2017-05-01
| Complete the Data Visualization(Kibana) requirements | WIP
Complete the Data Transformation(Spark) requirements
Complete the Data ingestion(Sqoop/Hive) requirements
2017-05-02
2017-05-03
2017-05-04
2017-05-05

## Dashboard Requirements
| Requirements | Data Requirements | Development Status
Dashboard name | Name of the dashboard is Casemanager. There should be a search screen on top and allow users to search based on any values eg:C201704*.Output should return with all the data with the input search value. If the input search value is not present , then it should return 'no results found'
Visualization1 | Create a Case summary with the below stats. Case Number Alert Count(s) : Case Name : Customer count : Transaction count(s) : Transaction total : Case Creation Date/Time : | Case Number should be of CYYYYMMNNNNN eg:C20170412345 Alert count,customer count and Transactions count contains only digit values Case Name contains only character values. Transaction total is of decimal type and $ should be prefixed before the amount eg:$4,656,171.50. Case creation timestamp should be of YYYY-MM-DD HH:MM:SS format. There shouldn't be any pencil or x mark in the viz board
Visualization2 | Create an Alert summary with the below stats. Case Number Alert Number : Scenario : Event Date : Alert Date: | Case Number should be of CYYYYMMNNNNN. Alert Number should be of ANNNNNNN eg:A1234567. Transaction total is of decimal type and $ should be prefixed before the amount eg:$4,656,171.50. Event Date & Alert Date is for format DD MMM YYYY
Visualization3 | Create a Case Similarity Summary with the below stats. Source Case # Target Case # Target Case Date Case Status Similarity Score Score calculation rules are explictly mentioned in the another tab | Similarity Score should be a value between 1 and 100.
Visualization4 | Create a Transaction Summary with the below stats. Transaction Alert Event Date Source Customer Target Customer Amount
Visualization5 | Create a Counterparty Prioritization with the below stats Counterparty Name Alert Number Customer ID CPR Score Transaction Count Total $ Amount Country Country Risk Score Transaction Count % Transaction Amount % Customer Risk Rating Number of Relationships Number of unique Scenarios triggered Adverse Media Score Round Dollor Amount % Round Dollor Transactions Count % Alerted Period ORG/BEN
Visualization6 | Create a Focal Entity section with below stats Address Other Address Customer Information Other Information
Visualization7
Visualization8
Visualization9
Visualization10

## mysql commands
create table testtable(case_id VARCHAR(30),case_identifier VARCHAR(30));
insert into testtable values(1234567,C201703021234567);

## Alert Similarity
Feature | Logic | Score
Same Focalentity between 2 alerts | Source alert m.CUSTOMER_ID = Target alert m.CUSTOMER_ID, where neither is NULL | 25
Same scenario between two alerts | Source alert CHECK_NAME = Target alert CHECK_NAME, where neither is NULL | 35
Same focal entity role between two alerts | Source alert m.CUSTOMER_ID and m.ENTITY_NAME = Target alert m.CUSTOMER_ID and m.ENTITY_NAME, where none are NULL | 25
Same counterparties between two alerts | Source alert m.ORIGINATOR_KEY and m.BENEFICIARY_KEY = Target alert m.ORIGINATOR_KEY and m.BENEFICIARY_KEY, where none are NULL | 15
Alert # | Customer # | Scenario
A123456 | 1000 | Scenario1
A123457 | 1000 | Scenario2
A123458 | 2000 | Scenario1
source_alert # | target alert | Customer # | Scenario
A123456 | A123457 | 1000 | Sce
A123456 | A123458 | 1000
25

## Data mapping
Vizboard1 | Target column name | Transformation | source column name | source table name
Case Number | Case Number | NA | case_identifier | cases
Alert Count(s) : | Alert Count | 1) cases join alert_case on (case_identifier) 2) alert_case join mon_alert(alert_key=id) 3) Get the count(distinct alert_identifiers) group by case_identifier | number_of_alerts | cases alert_case mon_alert
Case Name : | Case Name | NA | case_description | cases
Customer count : | Customer Count | hardcode as 0 |  | cases
Transaction count(s) : | Transaction Count | 1) mon_alert join transactions on (alert_identifier) 2) Get the count(distinct txn_id) group by case_identifier |  | cases alert_key mon_alert
Transaction total : | Transaction Total | 1) mon_alert join transactions on (alert_identifier) 2) Get the count(txn_amount_orig) group by case_identifier |  | cases alert_key mon_alert transactions
Case Creation Date/Time : | Case timestamp | NA | creation_timestamp | cases
Viizboard2 | Target column name
Case Number | Case Number | NA | case_identifier | cases
Alert Number | Alert Number | 1) cases join alert_case on (case_identifier) | alert_identifier
Scenario | Scenario | NA | check_name | mon_alert
Event Date | Event Date | NA | event_date | mon_alert
Alert Date | Alert Date | NA | alert_score_date | mon_alert